| Year | Canterbury City Council Local Plan | Bridge Parish Council | NP Committee | Editions of plan (those published to the public in bold) | Context of NP | Key elements of plan composed/revised |
| --- | --- | --- | --- | --- | --- | --- |
| 2005 |  |  |  | Bridge Parish Plan published |  |  |
| 2011 |  | May Elections: Cllr Hill- Chair |  |  | Localism Act |  |
| 2012 |  |  | NPC set up-Prof. Joe Connor-Chair. Clerk=villager Esther Hall |  | 8 Affordable houses occupied on Brickfields-7 years after initial plans were laid | Questionnaire to all villagers- “small scale developments” to be encouraged. Objectives drawn up |
| 2013 | CDLP drafted and consulted upon Planning inspector Mr Moore refers to Bridge and the emerging NP | Cllr Hodges-Chair |  |  |  | Objectives finalised |
| 2014 |  |  |  | October 2014 |  | Parking Survey. Draft NP published and consulted upon |
| 2015 |  | May Elections: Cllr A Atkinson-Chair |  |  |  | Autumn: Housing became a key focus for the emerging plan-first Cantley proposals. |
| 2016 |  |  |  |  | May: Planning consultant Jim Boot engaged by the Parish Council, using DCLG grant monies to pay his fees. In post until Spring 2018 | Housing continues to be discussed. 8 July: Cantley limit housing sites to 2. |
| 2017 | July-CDLP adopted with no housing allocated for Bridge. Green Gap is formally adopted as part of the CDLP |  | Jan 2017?? NPC chaired by Cllr A Atkinson and clerked by Parish Clerk. Formally set up as an advisory committee of the Parish Council. | August (draft 6) |  | Traffic count completed (Jan) Green Spaces, Village Design Statement consulted upon (Jan) Health check on NP published May-June: AECOM scoping report published and consulted upon with statutory consultees Housing needs survey done and results published (June/July 2017) Green Gap in CDLP precludes Conyngham Lane housing site. 8 August: Cantley confirm this. Autumn: Cantley final housing proposals published (Appendix F) to villagers by post 1-3 November 2017 |
| 2018 | February June Sept Oct/Nov |  |  | Regulation 14 edition (known as draft 9) Regulation 15 –NP to CCC Regulation 16 edition |  | AECOM SEA published Feb 2018 Draft plan examined |
| 2019 |  | May Elections |  |  |  |  |

The Inspector, Mr Moore, whose hearings were held in Autumn 2016,  when assessing the most recent CDLP  wrote  (CDLP point 253) that “In the context of the size of the village and the general extent of the AONB, the scale of the development proposed could not be described as major.“ This was for the 40 homes proposed for the village by Canterbury district at the Brickfields site which was within the AONB.    At point 254, Mr Moore wrote “….The most appropriate location for further development in Bridge is a matter that could be addressed in the NP.”

August 2017 version (draft 6) added Gt Pett Farm policy (A3);   refers to the now completed housing survey;   indicates that the preferred housing site (C3) is not yet agreed; added policy F2 on light pollution   P.26 of this draft outlined work still to be done.