Timeline and documentary proof of consultation.  Bridge Neighbourhood Plan 2012-2018

(Shaded rows indicate that consultation was not taking place and therefore changes in the Neighbourhood Plan did not necessarily follow)

NPC= Neighbourhood Planning Committee

CCC=Canterbury City Council

NP=Neighbourhood Plan

CDLP= Canterbury District Local Plan

| Date | NPC meeting | Evidence | Electronically held? | Analysis available | % response | Changes made as a result of feedback given (Italics indicate a learning point for the NPC or a change to procedures which did not directly affect the composition of the plan itself) |
| --- | --- | --- | --- | --- | --- | --- |
| 26.01.2012 |  | Clerk’s first notes on NP process | √ |  |  |  |
| 19.04 2012 | √ | Plans set for questionnaire to village residents-before production of first draft. |  |  |  |  |
| 20.04.2012 |  | Letter to Adrian Verrall of CCC-he had visited NPC earlier that month |  |  |  |  |
| 8.06.2012 |  | Closing date for receipt of questionnaire returns. Questionnaire covers new housing, car parking and green spaces. |  |  |  |  |
| 19.06.2012 |  | 335 replies received to June 2012 questionnaire. 50/50 split on more housing. 720 issued-one to each household. |  | √ | 47% | See below for 25 August 2012 |
| 7.7.12 |  | Formal request by NPC to CCC to register the NP |  |  |  |  |
| 31.7.2012 | √ |  |  |  |  |  |
| 09.8.2012 | √ |  |  |  |  |  |
| 20.08.2012 | √ |  |  |  |  |  |
| 25 August 2012 |  | Village Hall exhibition showing results of questionnaire- a list of relevant issues emerged from this. |  |  | 47% | Insufficient provision for cyclists in Bridge (appeared in the final 2018 Regulation 16 NP as policy B1). Strong resistance to expansion of the school (76% of respondents)-explains project D2 in the final 2018 Regulation 16 NP plan. |
| 30.08.2012 |  | CCC has no objection to NP area nor to the Parish Council bringing one forward | √ |  |  |  |
| 21.09.2012 | √ |  |  |  |  |  |
| 09.10.2012 | √ Stella Meesters from Planning Aid |  |  |  |  | Stella outlined the limitations of a NP to the committee-what it can and cannot achieve for a local community |
| 25 October 2012 |  | BNPC committee members meet Adrian Verrall-as still no response to letter of 7 July 2012 had been received. |  |  |  |  |
| 05.04.2013 | √ |  |  |  |  |  |
| 26.04.2013 | √ |  |  |  |  |  |
| 24.05.2013 | √ |  |  |  |  |  |
| Spring 2013 |  | Parish newsletter to all households outlines the NP to villagers |  |  |  |  |
| 1.06.2013 |  | Village Hall exhibition representing results of August 2012 questionnaire |  |  | 102 residents attended. 42 questionnaires returned. | Exhibition invited villagers to raise issues to be placed in the NP. - By November 2013 these resulted in draft objectives for the NP (NPC meeting of 15 Nov 2013 ) - The creation of a website (13 December 2013 meeting of the NPC) |
| 11.06.2013 | √ |  |  |  |  |  |
| 25.06.2013 |  | School Fete exhibition | √ | √ |  | Repeated the exhibition of 1 June 2013 @ Bridge Primary School |
| June 2013 |  | Village Design Statement published | √ |  |  |  |
| July 2013 |  | Approval accorded by CCC for a NP to be prepared |  |  |  |  |
| 08.07.2013 | √ |  |  |  |  |  |
| 09.08.2013 | √ Stella Scrivener from Planning Aid |  |  |  |  | Underlined need to separate policies from projects. |
| September 2013 |  | NP article for Parish news-update on NP progress |  |  |  |  |
| 13.09.2013 | √ |  |  |  |  |  |
| 24.10.2013 |  | Invite from NPC chair to villagers via parish magazine to join the NPC. |  |  |  |  |
| 15.11.2013 | √ |  |  |  |  | Deletion of initial references in the emerging plan to the Oil Depot site. |
| 13.12.2013 | √ |  |  |  |  |  |
| 10.01.2014 | √ Stella Scrivener from Planning Aid |  |  |  |  | Underlined need to separate policies from projects. Guidance on composition of a typical NP and common pitfalls to avoid. |
| 14.02.2014 | √ |  |  |  |  |  |
| 14.03.2014 | √ |  |  |  |  |  |
| 11.04.2014 | √ |  |  |  |  |  |
| 08.05.2014 | √ Adrian Verrall (CCC) |  |  |  |  |  |
| May 2014 | Parking Survey | Paper | √ | 110 residents + 21 non residents responded |  | Led to policies B4 and B5 in the October 2014 draft, now project B5 in the final regulation 16 2018 consultation document. Parking is also addressed in Appendix F of the 2018 regulation 16 consultation document. |
| 13.06.2014 | √ |  |  |  |  |  |
| 11.07.2014 | √ |  |  |  |  |  |
| 29.08.2014 | √ |  |  |  |  |  |
| 19.09.2014 | √ |  |  |  |  |  |
| 03.10.2014 | √ |  |  |  |  |  |
| October 2014 |  | First Consultation Draft issued by 21 volunteers with covering letter to all households |  |  |  |  |
| 20.10.2014 |  | Comments from Stella Scrivener (Planning Aid) on October 2014 draft |  |  |  | These comments were reviewed at NPC meetings in Jan and Feb 2015 |
| 1 November 2014 |  | Consultation event –BVH-10-1 p.m. |  |  |  | 21 November 2014 minutes of the NPC record a need –expressed in the consultation-to - add a page showing membership of the committee. - publish minutes on website - to explain abbreviations used |
| 21.11.2014 | √ |  |  |  |  |  |
| December 2014 |  | Village poster encouraging responses to the ongoing consultation |  |  |  |  |
| 15.12.2014 |  | Deadline for receipt of comments on first consultation draft |  |  |  |  |
| 23.01.2015 | √ |  |  | 131 responses based on the October 2014 draft |  | All sections of the plan to be reviewed in light of the comments received and analysed by Mr Esdale. - Section on housing is deemed by many to be contradictory and to be rewritten collectively. - All other sections of the plan given to an NPC member to review. |
| 27.02.2015 | √ |  |  |  |  |  |
| 10.04.2015 | √ |  |  |  |  |  |
| 02.09.2015 | √ |  |  |  |  |  |
| 13 and 20 October 2015 |  | Information events on housing proposals held in Parish Church-with questions recorded and answered as given recorded by the Clerk |  |  |  | Access to proposed housing site in Appendix F of the 2018 final regulation 16 version is presaged by a comment made by a villager at the event on 13 October. |
| 12.11.2015 | √ |  |  |  |  |  |
| November 2015 |  | Version 1.5 of the plan completed |  |  |  |  |
| 12.02.2016 | √ |  |  |  |  |  |
| 23.02.2016 | √ |  |  |  |  |  |
| 20 and 22 March/April 2016 |  | 2 Village hall consultations about site preferences for housing | √ | √ |  |  |
| 11.04.2016 |  | Deadline for return of housing preference forms | √ |  | 14% | Preferences expressed for Site 2 (Conyngham Lane) then for Brickfields then for site 4 (recreation ground near the surgery). Full analysis to be found at: www.bridgevillage.org.uk/NHP/index.asp Go to “documents” and click on “NPC Reports & papers.” and then open the file entitled “ 2016 04 April NP” |
| 25.04.2016 | √ |  |  |  |  |  |
| 28.04.2016 |  | Annual Parish Meeting-feedback on NP given | √ |  |  |  |
| 06.05.2016 | √ |  |  |  |  | Record made of changes made to Section C of the plan. |
| 27.05.2016 | √ |  |  |  |  |  |
| 10.06.2016 | √ |  |  |  |  |  |
| June 2016 |  | Rural community profile received from ACRK | √ |  |  | Profile added as Appendix D to the NP. |
| June 2016 |  | Appointed Jim Boot as advisor |  |  |  |  |
| 25 June 2016 |  | School fete display on NP | √ | √ | 56 respondenets. | The clear outcome of this consultation was that the Conyngham Lane site for housing was not popular. 29 negative comments about this site: just 9 in favour. In marked contrast to the consultation carried out in March 2016 (above). |
| 26 July 2016 | Met with CCC planners |  |  |  |  | Cathy McNab of CCC suggested sustainability appraisals of sites considered for inclusion in the NP. This idea was adopted . This meeting led to the emergence of policy A3 regarding Great Pett Farm. |
| 29 July 2016 | √ |  |  |  |  | CCC reportedly have made it clear they would like Recreation Ground sites considered for housing. This became NP policy after August 2017 (see below). |
| 25 August 2016 | √ |  |  |  |  | Decision taken to carry out sustainability appraisals-later emerged in the final regulation 16 version of the NP as Appendix B |
| 30 September 2016 | √ |  |  |  |  | Up to date flood map provided by the Environment Agency-for inclusion in the final version of the plan-though a version dating May 2018 was eventually included in the NP |
| 13 October 2016 | Met with CCC planners |  |  |  |  | Checklist of all aspects of the N Plan and conformity with emerging CDLP and other suggestions offered. The document is available here www.bridgevillage.org.uk/NHP/index.asp Go to “documents” and click on “Click here for all Neighbourhood Plan Committee (NPC) agendas, minutes, reports etc.” and then open the folder entitled “NPC docs” |
| 28 October 2016 | √ |  |  |  |  | CCC suggestion that a cycle route plan is added to the plan is adopted. Now policy B1 of the NP. |
| 25 November 2016 | √ |  |  |  |  | Checklist of requests made by CCC in October 2016 and their implementation within the plan (19 of these in total covering all sections of the plan). |
| December 2016 |  | Update to all villagers via the website on progress of the NP written by consultant Jim Boot-summarising work from June to December 2016 | √ |  |  |  |
| Dec 2016 |  | Met with CCC planners |  |  |  |  |
| December 2016 |  | Health check with Claire Tester-published on the NP website | √ |  |  | Housing allocations to be made within the NP-though a Strategic and Environmental assessment will be needed. Clearer distinction made between policies and projects as a result of her comments and the use of different colours to denote policies and projects within the plan. |
| 6 Jan 2017 | Minutes of NPC |  |  |  |  | Outlines new constitution of the Committee. Brickfields site is no longer supported by inspector examining the CDLP. He (Mr Moore) also announced that he would expect the emerging NP to determine where housing in Bridge should be located. |
| w/c 9 January 2017 |  | Traffic survey conducted |  |  |  | Results fed into the NP. (It now sits within the evidence section of the Plan). Speed as recorded in the survey are well within the range of 20 mph as required by Kent Highways (as revealed in minutes of NPC dated 30 September 2016) |
| 12 January 2017 |  | Bridge Parish Council meeting |  |  |  | Minute 110/16-17 (11) sets out the new governance issues for the NPC-agreed to by all Parish Councillors present. |
| 17 January 2017 | Met with CCC planners |  |  |  |  |  |
| 20 January 2017 |  |  |  |  |  | NPC committee meeting decided to revise the employment section in the plan as a result of communication from Cantley about their plans for Great Pett Farm. |
| 21 January 2017 |  | Village hall consultation on green spaces |  |  |  | Photos of 14 proposed green spaces were on display as well as a copy of the Tester Health Check report of December 2016 and the village design statement. Draft 5 of the plan was also available. |
| 24 Feb |  |  |  |  |  | NPC meeting told that AECOM are likely to be employed and paid for by public grant to do the Strategic Environmental Assessment. NPC is moving away from support for the Conyngham Lane site |
| 14 March 2017 | Met with CCC planners |  |  |  |  |  |
| March and June |  |  |  |  |  | NPC raises doubts about the proposed Conyngham Lane site. No decision taken as such but Cantley proposals alter the whole issue. (see below August 2017)as did the adoption of the CDLP in July 2017 and the strategic policy referring to the green gap between Bridge and Canterbury |
| 27 April 2017 |  | Annual Parish Meeting-feedback given on NP. | √ |  |  |  |
| April 2017 |  | Further advice received from Claire Tester re the NP |  |  |  | Her advice to conduct site assessments for the housing sites becomes part of the AECOM SEA report. |
| 23 May 2017 | Met with CCC planners |  |  |  |  |  |
| 26 May 2017 |  | First meeting of reconstituted NP Committee |  |  |  |  |
| June 2017 |  | Housing needs survey distributed to all households |  |  |  | Results fed directly into the NP as Appendix C |
| 13 July 2017 |  | Canterbury City Council adopts its local plan |  |  |  | Green gap is now confirmed in the CDLP. Proposals for housing in Conyngham Lane do not conform. |
| August 2017 |  | Cantley withdraw housing site in Conyngham Lane and propose site as shown in Appendix F |  |  |  | Adopted into the plan as Appendix F-along with suggested sites for village hall. |
| 4 October 2017 | Met with CCC planners |  |  |  |  |  |
| 15 January 2018 | Met with CCC planners |  |  |  |  |  |
| Feb 2018 |  |  |  |  |  | Aecom produce updated version of their Strategic Environmental Assessment for Regulation 14 consultation. |
| Feb-April 2018 2 public exhibitions were held on Sunday 18 March 2-5 p.m. and Saturday 7 April 5-8 p.m. in the village hall- villagers could gain more information about the consultation plan from members of the committee. | . | Regulation 14 consultation Printed copies of the NP, the consultation response form and the appendices were available. Events advertised on village website, social media and noticeboards. |  | 50 or so comments received 28 villagers attended over both days. |  | According to CCC the Basic Conditions statement is “sufficiently thorough”. The regulation 14 consultation responses document is available here www.bridgevillage.org.uk/NHP/index.asp Go to “documents” and click on “”NPC Reports & papers.” and then open the file entitled “2018 06” At its meeting on 8 May 2018 the committee agreed revisions to the plan as a result of the Regulation 14 consultation. The NPC worked through all the changes to the plan line by line. They were very minor and of no consequence to the Plan since those who agreed or strongly agreed with all aspects of the plan were in a clear majority in all of the responses. |
| 3 May 2018 |  | 2 CCC planners walked the village with members of the committee to review the proposed green spaces. |  |  |  | Suggestions from the CCC planners were adopted to reduce the number of green spaces to include only those now contained within the regulation 16 2018 version of the NP (reduced from the 12 potential green spaces outlined in the NPC meeting of 28 October 2016) |
| 8 May 2018 | √ |  |  |  |  |  |
| 10 May 2018 |  | Parish council voted to adopt fully the regulation 15 version of the plan. |  |  |  |  |
| 16 May 2018 | √ |  |  |  |  |  |
| 12 June 2018 |  | Meeting with CCC |  |  |  | Basic Conditions Statement judged to be satisfactory. Paragraphs need to be numbered-this revision was made and is to be found in the final regulation 16 version of the NP |
| 18 June 2018 | √ |  |  |  |  |  |
| 12 July 2018 |  | Parish council voted to adopt fully the regulation 16 version of the plan |  |  |  |  |
| 6 July - 7 September 2018 |  | Regulation 16 consultation |  |  |  | Policy C1 (m) amplified. (requested by CCC) Policy C7 (second sentence added)(requested by CCC). p. 25 –green spaces numbered (requested by inspector) p.27 new pictures and views added to illustrate more accurately the narrative in the text (requested by Inspector) (All decided at 16 October 2018 meeting) |
| 16 October 2018 | √ |  |  |  |  |  |

Philip Wicker  Clerk to Bridge Parish Council

23 October 2018

Further stakeholder discussions:

| Letter to | Sent on | Reply received |
| --- | --- | --- |
| Highland Investment Co Ltd | 01.03.2014 | 18.03.2014 |
| Savills | 15.06.2012 |  |
| CCC Estates dept | 01.03.2014 |  |
| Dental practice | 12.06.2012 |  |
| Health Centre | 06.09.2013 | 16.10.2013 |
| Owners of all shops in Bridge (including Pharmacy, Post Office, Woodlands, Bridgeway Stores, Nicholas James, Alfie and Trish photography, Laurie Wakeham) | 12.06.2012 | 06.07.2012 (one and only reply received) |
| Bridge School | 12.06.2012 |  |
|  | 08.04.2013 | 18.04.2013 |
|  | 06.09.2013 |  |
| Roger’s Garage | 10.03.2014 |  |
| Mr V Macdonald (landowner) | 01.03.2014 | By email |